## Q1-22 Sprint 1
Summary | ID | Status 4-6-2022 | Status 4-13-2022 | Status 4-20-2022 | Final Status
Basic Get Signature from Customer Messages - Ingenico | B-54430 | Likely
ELERA Pay Report - Validation/Verification | B-72317 | Likely
Synchronize Date/Time with Verifone PIN Pad | B-59724 | Testing
PIN Pad SW Upgrades - client - VERIFONE | B-71554 | TBD
Integration testing story for software upgrade | B-73548 | Likely
Update Forms for Pin Pads to New Elera Pay Logo | B-73665 | Testing
Remove Spring dependencies from ELERA client | B-74013 | Testing
Testing - Allow Customer to Swipe a Loyalty Card - Ingenico | B-73919 | Likely
Stored Value Card Service Enhancements - ValueLink | B-62111 | Likely
EMV Certification support | B-73995 | Likely
Client SAF - adapter changes | B-71620 | Likely
BIN Lookup/s/w update | B-73883 | Likely
Basic Get Numeric Input from Customer Messages | B-54926 | Likely
Value Card Support - generate receipt block | B-69059 | TBD
Client SAF - offline-payments service enhancements | B-71619 | TBD
Implement SAF/TOR throttling logic | B-59938 | TBD

## Defect Status
Title | ID | Previous Week | Current Status
PIN PAD not requesting the PIN for refunds transactions | D-13265 | Awaiting Resolution | Awaiting Resolution
Approved EMV card displays contradictory remove card followed by leave card in pinpad dialog | D-13164 | Awaiting Resolution | Resolved
Pinpad dialog is not updated when leaving Elera order screen | D-13216 | Awaiting Resolution | Resolved
Verifone-PINPAD rejecting contactless/insert of EMV card | D-13663 | Awaiting Resolution | Awaiting Resolution
Gift card swipe after timeout will cause system to hang | D-12045 | Awaiting Resolution | Awaiting Resolution
Ingenico - Not able to cancel a ManualPanEntry from red button | D-13360 | Awaiting Resolution | Awaiting Resolution
Ingenico - "Error reading Card" error is displayed when press X red button on Expiration date or CVV screen | D-12133 | Awaiting Resolution | Awaiting Resolution
Handle voids of STAR Access transactions | D-11997 | Awaiting Resolution | Awaiting Resolution
Documentation only - Ingenico Link 2500 is not able to show Scrolling Receipt | D-13843 | Awaiting Resolution | Awaiting Resolution
Generate correct 8A value for offline EMV payments | D-14752 | NEW | Awaiting Resolution